## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Emily | Nehesia | Komila | Jash | Cheyenne | Geetika | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 12 |  | 0
Iteration 1 |  | Design architecture | Design Architect | Francois, C. | 12 |  |  |  |  | 0 | 0 |  | 8 | 0
| Requirements |  |  |  |  | 9 |  | 8
|  | Gather | Requirements Engineer | Wiehe, K. | 2 |  | 2 |  |  | 0 | 2 |  |  | 0
|  | Analyze | Requirements Engineer | Wiehe, K. | 4 |  | 3 |  |  | 0 | 3 |  |  | 0
|  | Specify | Requirements Engineer | Wiehe, K. | 3 |  | 3 |  |  | 0 | 3 |  |  | 0
| Documentation |  |  |  |  | 33 |  | 23.6
|  | Project Charter | Project Manager | Edmond, N. | 4 |  | 4.5 |  |  | 4.5 | 0 |  |  | 3
|  | Release Plan | Project Manager | Edmond, N. | 3 |  | 1.3 |  |  | 1.3 | 0 |  |  | 1.3
|  | Requirements Document | QA, Requirements Engineer | Wiehe, K. Foley, E. | 5 |  | 2 |  |  | 0 | 2 |  |  | 0
|  | Project Plan | Project Manager | Edmond, N. | 8 |  | 8.3 |  |  | 8.3 | 0 |  |  | 4
|  | Architecture Document | Project Manager | Edmond, N. | 4 |  | 4 |  |  | 4 | 0 |  |  | 0
|  | Test Report | Tester | Foley, E. | 4 |  | 1 |  |  | 0 | 0 |  |  | 2
|  | User Guide & System Admin Doc | Lead Developer, Requirements Engineer | Edmond, N., Wiehe, K. | 5 |  | 2.5 |  |  | 4 | 2.5 |  |  | 0
Coding
Iteration 2: | Development |  |  |  |  | 35 |  | 61
|  | Determine technology needs | Developer | Singh, J. | 4 |  | 1 |  |  | 2
|  | Research and learn new language and environment | Developer | Singh, J. , Francois, C. | 10 |  |  |  |  | 3 |  |  | 10
|  | Set up proxy server software | Developer | Edmond, N. | 3 |  | 1 |  |  | 1
|  | Write basic proxy code | Developer | Padamati, G. Edmond, N. | 5 |  | 7 |  |  | 7
|  | Implement classes | Developer | Padamati, G. Edmond, N. | 2 |  | 1 |  |  | 1
|  | Create HTTP handling code | Developer | Padamanti, G. Edmond, N. | 3 |  | 1 |  |  | 1
|  | Write code to store user name via database | Developer | Francois, C. |  |  | 6 |  |  | 0 |  |  | 8
|  | Write code for managing HTTP session | Developer | Edmond, N. | 3 |  | 3 |  |  | 3
|  | Unit Testing | Developer | Foley, E. | [5 empty] | 0
|  | Build ER diagram | Developer | Wiehe, K. Singh, J. | 5 |  | 5 |  |  | 0
Analysis
|  | System Testing | Tester | Foley, E. | 5 |  |  |  |  | 0
|  | Bug fix as required | Tester, Developer | Foley, E. | 5 |  |  |  |  | 0
|  | Evaluate needs for next iteration | Project Manager | Edmond, N. | 3 |  | 2 |  |  | 2
Iteration 3: | Design | [6 empty] | 21
|  | Implement any design changes | Project Manager, Developer | Edmond, N. | 6 |  | 2 |  |  | 2
|  | Risk analysis | Project Manager | Edmond, N. | 2 |  | 4 |  |  | 4
|  | Design XML format | Design Architect, Software Architect | Francois, C. Padamati, G. | 3 |  |  |  |  | 0 |  |  | 2
|  | Create SQL Code for log in | Developer | Francois, C. | 4 |  | 7 |  |  | 0 | 5 |  | 4
|  | Create UI design for home screen | Developer | Edmond, N. | 7 |  | 8 |  |  | 8
Development
|  | Review requirements | Requirements Engineer | Wiehe, K. | 2 |  | 2 |  |  | 0 | 2
|  | Create SQL Code for notifications | Developer | Wiehe, K. Singh, J. | 7 |  | 8 |  |  | 0 | 8
|  | Handle data structure for retrieving user info | Developer | Foley, E., Padamati, G. | [5 empty] | 0
|  | Implement UI for dashboard | Developer | Foley, E., Padamati, G. | [5 empty] | 0
|  | Unit Testing | Tester | Foley, E. | [5 empty] | 0
Analysis
|  | System Testing | Tester | Foley, E. | [5 empty] | 0
|  | Bug fix as required | Tester,Developer | Foley, E. | [5 empty] | 0
|  | Evaluate needs for next iteration | Project Manager | Edmond, N. | 3 |  | 3 |  |  | 3
Iteration 4 & 5: | Design
|  | Implement any design changes |  | Wiehe, K. | 2 |  | 2 |  |  | 0 | 2
|  | Risk analysis |  | Edmond, N. | 5 |  | 6 |  |  | 6
|  | Create UI design for user dashboard |  | Padamati, G | [5 empty] | 0
|  | Link userdashboard and home page |  | Edmond, N. | 5 |  | 8 |  |  | 8
Development
|  | Review requirements | Requirements Engineer | Wiehe, K. | 2 |  | 2 |  |  | 0 | 2
|  | Develop code/ UI for user registration |  | Singh, J. | 7 |  |  |  |  | 0
|  | Implement notifications features |  | Wiehe, K. Padamati, G | 3 |  | 2 |  |  | 0 | 2 |  | 1
|  | Display user account information |  | Francois, C., Foley E. | [5 empty] | 0
|  | Unit Testing | Tester | Foley E. | [5 empty] | 0
Analysis
|  | Acceptance Testing | Tester,Developer | Foley E. | [5 empty] | 0
|  | Bug fix as required | Tester, Developer | Foley E. | [5 empty] | 0
Total |  |  |  |  | 160 | 89 | 106.6 | 113.6 | 0 | 73.1 | 33.5 | 0 | 31 |  | 106.6