## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Emily | Nehesia | Komila | Jash | Cheyenne | Geetika | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 12 |  | 0
Iteration 1 |  | Design architecture | Design Architect | Padamati, G. | 12 |  |  |  |  | 0 | 0
| Requirements |  |  |  |  | 9 |  | 8
|  | Gather | Requirements Engineer | Wiehe, K. | 2 |  | 2 |  |  | 0 | 2
|  | Analyze | Requirements Engineer | Wiehe, K. | 4 |  | 3 |  |  | 0 | 3
|  | Specify | Requirements Engineer | Wiehe, K. | 3 |  | 3 |  |  | 0 | 3
| Documentation |  |  |  |  | 33 |  | 18.6
|  | Project Charter | Project Manager | Edmond, N. | 4 |  | 4.5 |  |  | 4.5 | 0
|  | Release Plan | Project Manager | Edmond, N. | 3 |  | 1.3 |  |  | 1.3 | 0
|  | Requirements Document | QA, Requirements Engineer | Wiehe, K. Foley, E. | 5 |  | 2 |  |  | 0 | 2
|  | Project Plan | Project Manager | Edmond, N. | 8 |  | 8.3 |  |  | 8.3 | 0
|  | Architecture Document | Design Architect, Software Architect | Padamati, G. Francois, C. | 4 |  |  |  |  | 0 | 0
|  | Test Report | Tester | Foley, E. | 4 |  |  |  |  | 0 | 0
|  | User Guide & System Admin Doc | Lead Developer, Requirements Engineer | Singh, J. Wiehe, K. | 5 |  | 2.5 |  |  | 0 | 2.5
Coding
Iteration 2: | Development |  |  |  |  | 0 |  | 0
|  | Determine technology needs | Developer | Singh, J.
|  | Research and learn new language and environment | Developer | Singh, J.
|  | Set up proxy server software | Developer | Edmond, N.
|  | Write basic proxy code | Developer | Padamati, G. Edmond, N.
|  | Implement classes | Developer | Padamati, G. Edmond, N.
|  | Create HTTP handling code | Developer | Padamanti, G. Edmond, N.
|  | Write code to store user name via database | Developer | Francois, C.
|  | Write code for managing HTTP session | Developer | Edmond, N.
|  | Unit Testing | Developer | Foley, E.
|  | Build ER diagram | Developer | Wiehe, K. Singh, J.
Analysis
|  | System Testing | Tester | Foley, E.
|  | Bug fix as required | Tester, Developer | Foley, E.
|  | Evaluate needs for next iteration | Project Manager | Edmond, N.
Iteration 3: | Design
Implement any design changes
Risk analysis
Design XML format
Design Perl XML-handling code
Create UI design for balance screen
Development
Review requirements
Create XML parsing code
Handle XML data structure for retrieving balance
Implement UI
Unit Testing
Analysis
System Testing
Bug fix as required
Evaluate needs for next iteration
Iteration 4: | Design
Implement any design changes
Risk analysis
Create UI design for vendor locations
Design data structure for RSS location list
Development
Review requirements
Develop code for processing vendor locations
Implement vendor map display
Display vendor information
Unit Testing
Analysis
Acceptance Testing
Bug fix as required
Total |  |  |  |  | 54 | 54 | 26.6 | 26.6 | 0 | 14.1 | 12.5 | 0 |  |  | 26.6